## Slide 1: Client Weekly Delivery Status - Checkout Modernization
AI-assisted delivery governance report

## Slide 2: Executive Delivery Summary
The Checkout Modernization project is currently 72% complete, with two key blockers identified. Our risk posture is moderate, driven by dependencies on external systems and pending product owner confirmation. To mitigate these risks, we recommend two leadership actions: firstly, expedite confirmation of tax calculation acceptance criteria to prevent downstream delays, and secondly, collaborate with the PSP sandbox team to resolve intermittent timeout issues impacting payment retry API validation. These actions will ensure the project remains on track to meet its objectives.
Scope: project:proj-checkout-modernization
Leadership Actions
- Escalate PSP support ticket and agree workaround for timeout simulations.
- Schedule product owner decision review and freeze UAT entry criteria.

## Slide 3: Delivery Status Dashboard
1
Projects
4
Updates
1
Approved
2
Blocked
72%
Avg Complete
Health Distribution
Green
2
Amber
2
Red
0
Interpretation
Green indicates on-track execution. Amber requires management follow-up. Red or blocker-backed items should be treated as escalation candidates for the next governance review.

## Slide 4: Team Status Detail
Person | Project | Period | Health | Complete | Key Update
Anya Rao | Checkout Modernization Platform | 20 Jul 2026 | Green | 78% | Completed wallet eligibility checks and improved checkout error handling. Feature flags...
Diego Martin | Checkout Modernization Platform | 20 Jul 2026 | Amber | 68% | Delivered payment retry API and telemetry hooks. Integration tests are stable except...
Nina Patel | Checkout Modernization Platform | 20 Jul 2026 | Amber | 70% | Completed regression plan, prioritized critical checkout journeys, and opened defects...
Marcus Lee | Checkout Modernization Platform | 20 Jul 2026 | Green | 72% | Sprint 8 remains within budget. UAT readiness is progressing with two decision items...

## Slide 5: Risks, Decisions, Next Actions
Checkout Modernization Platform
Risk: Timeline risk if PSP stability is not resolved before Sprint 9 hardening.
Action: Escalate PSP support ticket and agree workaround for timeout simulations.
Checkout Modernization Platform
Risk: Defect closure may slip without product owner decision on rounding tolerance.
Action: Schedule product owner decision review and freeze UAT entry criteria.