## Slide 1: Client Weekly Delivery Status - Order Management Modernization
AI-assisted delivery governance report

## Slide 2: Executive Delivery Summary
Delivery position: The Order Management Modernization project is 81% complete on average, with one contributor reporting a green health status and three reporting amber, indicating progress toward key milestones.
Risk posture: Two blockers have been identified, including the client security team's pending approval of the token rotation approach and the need for faster product owner turnaround in defect triage.
Leadership actions: To maintain momentum, leadership should prioritize facilitating the client security team's approval of the token rotation approach and ensuring timely product owner input for defect triage, enabling the project to stay on track for peak-season readiness.
Scope: project:proj-oms-modernization
Leadership Actions
- Director to secure client security decision by Wednesday governance call.
- Set daily defect triage with client product owner until UAT exit.

## Slide 3: Delivery Status Dashboard
1
Projects
4
Updates
1
Approved
2
Blocked
81%
Avg Complete
Health Distribution
Green
1
Amber
3
Red
0
Interpretation
Green indicates on-track execution. Amber requires management follow-up. Red or blocker-backed items should be treated as escalation candidates for the next governance review.

## Slide 4: Team Status Detail
Person | Project | Period | Health | Complete | Key Update
Anya Rao | Order Management Modernization | 20 Jul 2026 | Green | 84% | Completed order exception queue and retry visibility widgets. UAT build is deployed...
Vikram Desai | Order Management Modernization | 20 Jul 2026 | Amber | 80% | Closed API contract review and published Kafka topic retention decision. Performance...
Nina Patel | Order Management Modernization | 20 Jul 2026 | Amber | 78% | UAT test pack is 65% executed. Six high-priority defects remain open, with three...
Marcus Lee | Order Management Modernization | 20 Jul 2026 | Amber | 81% | Sprint 11 remains within budget tolerance. Peak-season readiness is achievable if two...

## Slide 5: Risks, Decisions, Next Actions
Order Management Modernization
Risk: Security approval delay can block production-readiness sign-off.
Action: Director to secure client security decision by Wednesday governance call.
Order Management Modernization
Risk: Open defect ageing may compress the final regression window.
Action: Set daily defect triage with client product owner until UAT exit.